## Pre-alpha
Project
P1579
Programmer
David Dixon
Quality Control Report
Functionality | Tested
User can trigger startup process that allows for access to and enables all features, and powers on equipment | TRUE
User can trigger shutdown process that stops and disables all features, and powers off equipment | TRUE
Automatic shutdown process that triggers the shutdown process at the end of the day in case the last users forget to shutdown the system | TRUE
Routing (Projector, Speaker Prg Audio, Speaker Bluetooth Audio) | TRUE
Audio controls (Speakers + Microphone Voicelift) | TRUE
Projector can be powered on/off | TRUE
Projector automatically power on when a video source is routed | TRUE
Controller navigation | TRUE
Camera Control (Manual) | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Issue | Status

## Internal
Project
Programmer (PGMR)
Quality Control Technician (Q.C.T.)
Internal
Quality Control Report
Issue (Reported by Q.C.T.) | Response (PGMR) | Status

## External
Project
Programmer (PGMR)
Quality Control Technician (Q.C.T.)
External
Quality Control Report
Issue (Reported by Q.C.T.) | Response (PGMR) | Status

## Introduction
Programming Quality Control Report Introduction
This report keeps track of all the program issus discovered during project. At the end of the project, the programmer will review this report and update the program template to address these issues (when applicable). The purpose of this process is to prevent this system's program issues from appearing in systems belonging to future projects. There are three individual sheets of this report to complete. 1. Pre-alpha. The programmer completes this section during the pre-alpha programming phase by themselves. Utilize the project programming document created during the pre-alpha programming phase to identify all the functionalities that need to be tested. 2. Internal. The internal quality control technician and programmer collaborate to complete this section during the internal quality control process. The technician records any discovered issues. Next the programmer addresses and resolves those issues. Lastly, the technician re-tests the system and confirms the issues have been resolved. This process will repeat until there are no more issues are discovered by the technician.
3. External. The external quality control technician and programmer collaborate to complete this section during the external quality control process. The technician records any discovered issues. Next the programmer addresses and resolves those issues. Lastly, the technician re-tests the system and confirms the issues have been resolved. This process will repeat until no more issues are discovered by the technician. This process will repeat until there are no more issues are discovered by the technician. Refer to the example sheets for guidance.

## Example (Pre-alpha)
Project
PXXXX
Programmer
Mr. PGRM
Quality Control Report
Required Functionality | Tested
User can trigger startup process that allows for access to and enables all features, and powers on equipment | TRUE
User can trigger shutdown process that stops and disables all features, and powers off equipment | TRUE
Automatic shutdown process that triggers the shutdown process at the end of the day in case the last users forget to shutdown the system | TRUE
Routing (Video, Audio, Control) | TRUE
Audio controls (Speakers, Microphones, Calls, etc.) | TRUE
Video Controls (Calls, Sharing, Scheduled Meetings, B.Y.O.D., Cameras, etc.) | TRUE
Video Endpoints (Displays, Projectors, Video Walls, etc.) can be powered on/off | TRUE
Microphone LEDs sync with mute state of calls | TRUE
Video Endpoints automatically power on when a video source is routed | TRUE
Controller navigation | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Issue | Status
Shutdown process wasn't powering off the display | Resolved
The user can get stuck on the navigation splash screen | Resolved
Audio routed was not following the last video source routed | Resolved
The microphone mute button was connected to the speaker mute | Resolved

## Example (Internal)
Project
PXXXX
Programmer (PGMR)
Mr. PGMR
Quality Control Technician (Q.C.T.)
Mr. QCT |  | Internal
Quality Control Report
Issue (Reported by Q.C.T.) | Response (PGMR) | Status
The projector won't power back on after powering off | Projector had a power saving setting that disabled network connections when powered off. Disabled that setting to prevent. | Resolved
The ceiling speakers audio volume level cannot be controlled from the controller | The Biamp instance tag in the program associated with controlling the volume speaker had a typo. | Resolved

## Example (External)
Project
PXXXX
Programmer (PGMR)
Mr. PGMR
Quality Control Technician (Q.C.T.)
Mr. QCT |  | External
Quality Control Report
Issue (Reported by Q.C.T.) | Response (PGMR) | Status
The projector screen comes down when the projector powers off, and up when the projector powers on | Projector screen contact closures were swapped during install. Swapped in program to match install. | Resolved
Scheduled meetings won't popuplate on the controller. | The meetings aren't being retrieved properly from the client's calendar. Recommend verifying client's calendar configuration is setup correctly. | Resolved
Users will be unaware they have to preface an outbound audio call number with the number 9 | Updated controller to include instructions to preface audio call phone numbers with 9. | Resolved